## Sheet1
Schedule 1b
EXAMPLE CONTRACTOR, INC.
CONTRACTS IN PROGRESS
For the year ended December 31, 20X4
|  | Contract to Date | [18 empty] | For the year ended December 31, 20X4 | [5 empty] | Backlog
Contract |  | Contract Amount |  | Estimated Gross Profit |  | Percent Complete |  | Earned Revenue |  | Cost to Date |  | Gross Profit | GP % |  | Progress Billings |  | Under Billings |  | (Over) Billings |  | Revenue Earned |  | Cost of Construction |  | Gross Profit |  | Revenue Remaining |  | Cost to Complete |  | Estimated Gross Profit
X311 | $ | 2733300 | $ | 164041 | $ | 87% | $ | 2377180 | $ | 2234512 | $ | 142668 | 6.002% | $ | 2525800 | $ |  | $ | -148620 | $ | 1809614 | $ | 1708095 | $ | 101519 | $ | 356120 | $ | 334747 | $ | 21373
X403 |  | 1375500 |  | 83152 |  | 88.6% |  | 1218207 |  | 1144564 |  | 73643 | 6.045% |  | 1219500 |  |  |  | -1293 |  | 1218207 |  | 1144564 |  | 73643 |  | 157293 |  | 147784 |  | 9509
X405 |  | 690000 |  | 43169 |  | 65.9% |  | 454597 |  | 426155 |  | 28442 | 6.257% |  | 492500 |  |  |  | -37903 |  | 454597 |  | 426155 |  | 28442 |  | 235403 |  | 220676 |  | 14727
X406 |  | 2245630 |  | 135149 |  | 22.9% |  | 514734 |  | 483756 |  | 30978 | 6.018% |  | 366900 |  | 147834 |  |  |  | 514734 |  | 483756 |  | 30978 |  | 1730896 |  | 1626725 |  | 104171
X408 |  | 322500 |  | 24873 |  | 59% |  | 190323 |  | 175644 |  | 14679 | 7.713% |  | 195500 |  |  |  | -5177 |  | 190323 |  | 175644 |  | 14679 |  | 132177 |  | 121983 |  | 10194
Jobs Under $100,000 |  | 1413280 |  | 155957 |  | 71.3% |  | 1007987 |  | 896755 |  | 111232 | 11.04% |  | 1023450 |  | 25177 |  | -40640 |  | 1007987 |  | 896755 |  | 111232 |  | 405293 |  | 360568 |  | 44725
| $ | 8780210 | $ | 606341 | $ | 65.6% | $ | 5763028 | $ | 5361386 | $ | 401642 | 6.969% | $ | 5823650 | $ | 173011 | $ | -233633 | $ | 5195462 | $ | 4834969 | $ | 360493 | $ | 3017182 | $ | 2812483 | $ | 204699
|  | Note D | [5 empty] | Note D | [6 empty] | Note D |  | Note D |  |  |  | Schedule 1
Note D
Work contracted for after December 31, 20x5 but before February 24, 20X5
X501 | $ | 1455656 |  | 87339 | [21 empty] | $ | 1455656 | $ | 1368317 | $ | 87339
X502 |  | 877650 |  | 70212 | [22 empty] | 877650 |  | 807438 |  | 70212
X503 |  | 89775 |  | 7182 | [22 empty] | 89775 |  | 82593 |  | 7182
X506 |  | 966750 |  | 58005 | [22 empty] | 966750 |  | 908745 |  | 58005
| $ | 3389831 |  | 222738 | [21 empty] | $ | 3389831 | $ | 3167093 | $ | 222738
See Report of Independent Certified Public Accountants on Additional Information
-20-